## Sheet1
Manage Comps |  | Rajeev estimation | Chaman estimation
| Designing framework |  | 6
| Download comps | Hours
1 | Selection of single values in Team, template, Sector, sub-sector, Portfolio | 4 | 4
2 | Selection of portfolio displays list of companies | 2 | 2
3 | Multiple selection of sub- sector | 2 | 2
4 | Multiple selection of portfolio | 2 | 2
5 | Removal of portfolio clears list of companies | 2 | 3
6 | Company selection through Search company option | 3 | 3
7 | a) when portfolio is not selected | 3 | 3
8 | b) when portfolio is selected but company not belongs to portfolio | 3 | 4
9 | c) when portfolio is selected but company belongs to same portfolio, verify validation message. | 3 | 5
10 | Addition of company displays it in list (item count also increases) | 2 | 4
11 | If company is active, it should not display lock icon in list | 2 | 2
12 | If company is locked, it should display lock icon in list | 2 | 2
13 | If a company is mapped to multiple portfolios, it should display only once in list | 2 | 4
14 | Reset functionality | 3 | 4
List of companies section
15 | Select all button | 2 | 3
16 | Deselecting any company deselect select all checkbox | 3 | 3
17 | View backup file action button (when file present and when not present) | 5 | 6
18 | Download backup files action button (when file present and when not present) | 10 | 10
19 | Deletion of company by action button ( verify company name and count after deletion) | 3 | 4
20 | Locking file manually by action button | 3 | 5
21 | Locking file will allow last downloaded file to get upload
22 | Verification- Only downloaded company can be locked | 3 | 3
23 | If company is not downloaded, validation message displays on locking | 2 | 3
24 | Lock company do not display lock icon | 2 | 2
25 | Verification of template column data with template | need to discuss | 5
26 | Verification of latest filling column data with template | 5 | 5
27 | Verification of updated date column data with template | 5 | 5
28 | Verification of B/S source column data with template | 5 | 5
29 | Verification of updated by column data with template | 5 | 5
30 | Check paging | 6 | 6
31 | Recently downloaded icon | 5 | 5
32 | Verification of data in recently downloaded dialog box
33 | Download button functionality | 3 | 4
Review shortlisted companies dialog box
34 | Select all button | 4 | 3
35 | Deselecting any company deselect select all checkbox | 5 | 3
36 | Verification of all columns data | 6 | 12
37 | Deleting company ( verify company name and count after deletion) | 3 | 4
38 | Check paging | 6 | 3
39 | Download comps button will download all selected file with a blank backup folder | 30 | 15
40 | Download backup button will download backup files | 5 | 10
41 | Downloaded companies will get lock icon dislaying |  | 5
42 | Unselected company downloaded will not lock it
Upload comps
43 | Upload comp file from select files | 25 | 2
44 | Click submit - starts process and gives message |  | 3
45 | Valid comp- Success message |  | 2
46 | Invalid comps- Validation message |  | 2
47 | a) Invalid extension |  | 2
48 | b) File not same as last downloaded |  | 2
49 | i) Verify template Id from last downloaded file |  | 1 | Control sheet
50 | ii) Verify version Id from last downloaded file |  | 1
51 | iii) Verify ticker from last downloaded file |  | 1
52 | iv) Verify ticker from last downloaded file |  | 1
53 | c) Company name is not correct |  | 2
54 | d) Ticker Id is not correct |  | 2
55 | e) Control sheet missing |  | 2
56 | Verify data in progress column when validation message appears |  | 3
57 | Verify data in progress column when success message appears |  | 2
58 | Upload backup files from Select files |  | 2
59 | Click submit - starts process and gives message |  | 2
60 | Valid backup file (Zip)- Success message |  | 2
61 | Invalid backup file (any other extension)- Validation message |  | 2
62 | Recently uploaded icon |  | 2
63 | Verification of data in recently uploaded dialog box
Trading Comps
| Select Company/Portfolio | 30
64 | Selection of single values in Sector, sub-sector, Portfolio |  | 2
65 | Selection of portfolio displays list of companies |  | 2
66 | Multiple selection of sub- sector |  | 1
67 | Multiple selection of portfolio |  | 1
68 | Visibility of selection in grid |  | 2
69 | Deletion of selection from grid clears list of companies |  | 2
70 | Company search through company radio button |  | 2
71 | Visibility of selection in grid |  | 2
72 | Addition of company in list (double click, visiblity in list and verify count) |  | 5
73 | Subsector/portfolio search through radio button |  | 2
74 | Visibility of selection in grid |  | 2
75 | Addition of company in list (double click, visiblity in list and verify count) |  | 5
| Shortlisted company section | 40
76 | Select all button |  | 2
77 | Deselecting any company deselect select all checkbox |  | 3
78 | Verification of B/S source column data with template |  | 4
79 | Verification of Last filling column data with template |  | 4
80 | Verification of Last updated date column data with template |  | 4
81 | Deleting company |  | 3
82 | Checking information |  | 3
83 | Reset functionality from Reset icon |  | 4
84 | Reset functionality from Reset button at bottom |  | 2
85 | Deleting multiple companies from delete button at bottom |  | 3
86 | Check paging |  | 2
87 | Click next when 1 portfolio is selected |  | 2
88 | Click next when multiple portfolios are selected |  | 2
89 | a) Select Final template dialog appears |  | 2
90 | b) Verify values in dialog box |  | 3
91 | c) Select 1 and click submit |  | 2
92 | Preview and generate comps tab opens |  | 2
93 | Visibility of output in image |  | 2
94 | Download comps button will download all selected file with a blank backup folder |  | 4
95 | Download comps with backup button will download backup files |  | 4